## Change Log
Date | Description | Editor(s) | Notes
2025-08-05 | Changes - Created Quartus project - Created RAM IP file initialized with Deliverable4.mif - Changed RAM.vhd in ModelSim project to be the new one | NW | Notes - Can just change the .mif file name inside RAM.vhd instead of going through wizard again - Design fully compiles in Quartus at this point - Not sure how many cycles need to wait for memory (1, 2, or 3?) because of the registers the IP catalog automatically added for the RAM. I'm guessing 1 or 2 prob. Bugs - Must change the configuration mode to "Single uncompressed image with memory initialization". I believe this is changed in Device -> Assignment (or similar) -> ... -> Device and Pin Options or something like that
2025-08-06 | Changes - Wrote tb_top_level.vhd Testing - Simulated using ModelSim - Validated Instruction Fetch functionality | NW | Notes - Did not use the memory viewer. Didn't need to yet - MemRead is asserted in one cycle then on the next cycle (on next rising edge), the read data can be seen on the output of the RAM. That is the RAM timing - Only need Quartus to get RAM IP file as far as I can tell. And for full synthesis Bugs - N/A
2025-08-15 | Changes - Made a couple of comments (night of 8/14/25) | NW | Notes - Bugs -
2025-08-16 | Changes - ALUOp: Changed ALUOp to be the same as IR31to26 aka the OP Code (updated top_level, Datapath, Controller, and alu_control entities) - CONTROLLER: Added and defined REG_FETCH, INST_DECODE, and R_TYPE states - ALU CONTROL: Added case for ADD 4 to PC, R-type inst, and ADDU inst | NW | Notes - Don't think I need to use any kind of states in ALU Control - NEXT STEP: Make controller/alu_control testbench Bugs - Haven't tested any of this yet but it compiles
2025-08-17 | Changes - Added testbenches tb_alu_control and tb_Controller for the alu_control and Controller, respectively. Tested out using these testbenches | NW | Notes - Decided on using the .mif file for integration testing and unit testbenches for unit testing - NEXT STEPS: Continue w/ simple R-types in alu_control. Skip to an I-type like addi so can load regfile with stuff. Test: Integration testing with .mif & unit testing with unit testbenches Bugs -
2025-08-17 | Changes - MODIFIED: alu_control.vhd, alu.vhd - ADDED: AND, OR, XOR, Shift right and left logical, and shift right arithmetic | NW | Notes - Haven't tested what you added to alu_control or alu yet, but it all compiles so far Bugs -
Night of 8/20/25 | Changes - MODIFIED: alu_control.vhd, alu.vhd - ADDED: Set on less than signed and unsigned | NW | Notes - Compiles Bugs -
2025-09-07 | Changes - MODIFIED: alu_control.vhd - ADDED: Signed multiplication, changed OpSel default to 0xFF | NW | Notes - Compiles. Haven't tested these changes yet Bugs -
| Changes - | NW | Notes - Bugs -

## VHDL Entities
Entity | Tested with Testbench
alu | In Progress
alu_control | In Progress
Controller | In Progress
Datapath | In Progress
enable_logic | Yes
Memory_top_level | Yes
mux2to1 | Yes
mux4to1 | Yes
PC | Yes
RAM | Yes
reg | Yes
registerfile | Yes
sign_extend | Yes
top_level | In Progress
Testbenches
tb_alu
tb_alu_control
tb_Controller
tb_Memory_top_level
tb_sign_extend
tb_top_level